## test_plan
Sl.no | Test | Description | Testcase name | Steps | Status
1 | sanity test | To check the connectivity between the design and testbench. | sanity_test
2 | Basic write/read test | To check basic write and read operation | w_r_test
3 | Interrupt generation | To generate interrupt, when counter reaches to 0. | interrupt_gen_test
4 | multiple write and read | To check multiple write operation followed by read | mul_w_r_test
5 | control reg test | To check the behaviour of timer by configuring different timer's operating modes. | ctrl_reg_test
6 | clock selection test | When EXTIN is selected as clock,it should be slower than half of the peripheral clock | clk_select_test
7
8
0

## covergae_plan
Functional_coverage
Covergroupname | Coverpoint | Bins | Description

## Sheet1
APB Timer Schedule
Start date -- 20-3-2024
End date -- 23-04-2024
S.no | Description | No of days
1 | Spec reading | 1
2 | Dv stratergy | 1
3 | Feature extraction and test plan | 1
4 | Test bench bring up | 1
5 | Development of driver logic | 2
6 | Sanity check between dut and testbench | 2
7 | Comparison logic-scoreboard development | 3
8 | Test case development as per the test plan | 6
9 | coverage | 3
10 | Checkers and assertions | 3
11 | Tb clean up | 2
12 | TODO,FIXME,COMMENTS
13 | Review
| Total days | 25 working days
Schedule will me modified according to the review comments